## Sheet1
UAT Create User Page #12
Script ID |  | 111222_1111 |  | Pre-Requisite Tasks |  |  | -
Test Type |  | User Acceptance Test |  | Estimated Effort to Execute |  |  | 30 mins
Predecessor Scripts |  | System testing |  | Data Requirement |  |  | Email, Password
Description/Summary |  | To test email and password validation on the 'Create User Page' |  | Script Data Supplied |  |  | 111_222_script_1
Objective/Expected Result |  | User is able to create an account on the 'Create User Page' |  | Comments |  |  | -
Priority (H/M/L) |  | M
Test ID | User | Test Description | Step Action(s) | Test Data | Expected Results | Actual Result | Test Status | Test Output (if relevant) | Bug ID | Comments
At Create User Page
1 | Accountless user | The system should not accept a password consisting of less than 8 characters, which of at least one uppercase letter, one lowercase letter and a digit. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter a valid e-mail address 4.Enter a password consisting of digits only. Enter a minimum of 8 digits. 5.Press “Create Account” | Email: test@acn.com Password: 12345678 | The user should return to the account creation page and receive an error message stating that the password is in the wrong format and displaying the required password conditions. | Provide Actual Result . . . . e.g. 1. The webiste is displayed 2. Error Displayed on Login Page | Not Run | Provide Test Output Here: e.g. Error 101 'Unauthorised Access' | Provide Bug ID, e.g: 111-222 | Provide Comments, e.g.: The test did not pass due to 'Unauthorised Access 'Error
2 | Accountless user | The system should not accept a password consisting of less than 8 characters, which of at least one uppercase letter, one lower case letter and a digit. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter a valid e-mail address 4.Enter a password consisting of lowercase letters only. Enter a minimum of 8 letters. 5.Press “Create Account” | Email: test@acn.com Password: abcdefgh | The user should return to the account creation page and receive an error message stating that the password is in the wrong format and displaying the required password conditions. | - | Not Run | - | - | -
3 | Accountless user | The system should not accept a password consisting of less than 8 characters, which of at least one uppercase letter, one lower case letter and a digit. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter a valid e-mail address 4.Enter a password consisting of uppercase letters only. Enter a minimum of 8 letters. 5.Press “Create Account” | Email: test@acn.com Password: ABCDEFGH | The user should return to the account creation page and receive an error message stating that the password is in the wrong format and displaying the required password conditions. | - | Not Run | - | - | -
4 | Accountless user | The system should not accept a password consisting of less than 8 characters, which of at least one uppercase letter, one lower case letter and a digit. | Pre-req: Steps: 1. Start the application 2. Click “Create Account” on the bottom of the start screen 3. Enter a valid e-mail address 4. Enter a password consisting of special characters only. Enter a minimum of 8 characters. 5. Press “Create Account” | Email: test@acn.com Password: !"#¤%&/( | The user should return to the account creation page and receive an error message stating that the password is in the wrong format and displaying the required password conditions. | - | Not Run | - | - | -
5 | Accountless user | The system should not accept a password consisting of less than 8 characters, which of at least one uppercase letter, one lower case letter and a digit. | Pre-req: Steps: 1. Start the application 2. Click “Create Account” on the bottom of the start screen 3. Enter a valid e-mail address 4. Enter a password consisting of less than eight characters. Enter a minimum of one uppercase letter, one lowercase letter and one digit. 5. Press “Create Account” | Email: test@acn.com Password: abc123C | The user should return to the account creation page and receive an error message stating that the password is in the wrong format and displaying the required password conditions. | - | Not Run | - | - | -
6 | Accountless user | The system should successfully register a user that enters a valid email and password when creating an account. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter a valid email. 4.Enter a valid password. 5.Press “Create Account” | Email: test@acn.com Password: abc123AB | The user should be logged in and redirected to the home page of the application. | - | Not Run | - | - | -
7 | Accountless user | The system should not accept an email address without a “@”, separating the local part from the domain. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3. Enter an email address without “@” 4. Enter a valid password 5.Press “Create Account” | Email: testacn.com Password: abc123AB | The user should return to the account creation page and receive an error message stating that the password is in the wrong format and displaying the required password conditions. | - | Not Run | - | - | -
8 | Accountless user | The system should not accept an email address without a top-level domain. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter an email address without a top-level domain following the mail server 4.Enter a valid password 5.Press “Create Account” | Email: test@acn Password: Abcd1234 | Email: test@acn Password: Abcd1234 |  | Not Run
9 | Accountless user | The system should not accept an email address without the local part and an email domain. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter an email address without the local email part, e.g. start the email with a “@” 4.Enter a valid password 5.Press “Create Account” | Email: @acn.com Password: Abcd1234 | The user should be presented a screen that says that the creation was unsuccessful due to the email not meeting the email requirements and given the option to enter a new email. | - | Not Run | - | - | -
10 | Accountless user | The system should not accept an email address without the local part and an email domain. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter an email address without the email domain, e.g. end the email with a “@” 4.Enter a valid password 5.Press “Create Account” | Email: test.acn@ Password: Abcd1234 | The user should be presented a screen that says that the creation was unsuccessful due to the email not meeting the email requirements and given the option to enter a new email. | - | Not Run | - | - | -
11 | User with registered account | The system should not accept two different users with the same email address. | Pre-req: Test Case 6 Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter an already registered email address 4.Enter a valid password 5.Press “Create Account” | Email: test@acn.com Password: Abcd1234 | The user should be presented a screen that says that the creation was unsuccessful because there is already a user with that email address. | - | Not Run | - | - | -
12 | Accountless user | The user needs to enter the same password twice to validate that the correct password is entered. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter a valid email address 4.Enter a valid password 5.Enter the same password in “confirm password” entry 6.Press “Create Account” | Email: test2@acn.com Password: Abcd1234 Password (confirm): Abcd1234 | The user should be presented a screen that says that the creation was successful. | - | Not Run | - | - | -
13 | Accountless user | The user needs to enter the same password twice to validate that the correct password is entered. | Pre-req: Steps: 1.Start the application 2.Click “Create Account” on the bottom of the start screen 3.Enter a valid email address 4.Enter a valid password 5.Enter a different password in “confirm password” entry 6.Press “Create Account” | Email: test2@acn.com Password: Abcd1234 Password (confirm): aBcd1234 | The user should be presented a screen that says that the creation was unsuccessful because the passwords do not match. | - | Not Run | - | - | -
Cycle | [5 empty] | Total effort to Execute
Overall Status | [5 empty] | Start Date
Scripted By | [5 empty] | End Date
Executed By | [5 empty] | Signature
Reviewed By